## Sheet1
Commodity | Country | Status |  |  |  |  | On hold | Action required/Notes
|  | Dossier under development | Year dosser submitted | Pest Risk Assessment (PRA) under review | Audit required? | Legislation drafting
Apple | Philippines |  | 2016 | ü | ü |  |  | Audit required prior to completion of access process
Apple | China |  | 2022 |  | ü |  | ü | China will only assess 1 application from a country at a time
Apple | Vietnam |  | 2025 |  | ü |  |  | Dossier submitted June 2025. Application under assessment.
Blueberry | Thailand |  | 2023 |  | ü | ü |  | Audit required prior to completion of access process
Celery | US |  | 2021 | ü |  | ü |  | UK consented to risk mitigation measures
Cherry | China |  | 2021 | ü | ü |  |  | Audit required prior to completion of access process
Cherry | Brazil |  | 2023 |  | ? |  |  | Application under assessment
Cherry | India |  |  | ü |  |  |  | Provided answers to additional questions from importing NPPO Nov 2025
Date palm plants | Paraguay | [6 empty] | Awaiting publication of import requirements
Hay/haylage | China | ü | [5 empty] | Dossier under development
Malus cuttings | US |  |  | ü |  |  |  | Awaiting risk mitigation measures from importing NPPO
Musa acuminata | Colombia |  | 2025 | ü |  |  |  | Dossier submitted October 2025. Application under assessment
Poplar logs | India |  | 2016 |  |  |  |  | Provided answers to additional questions from importing NPPO Dec 2025
Potato mini tubers from Scotland | US |  | 2009 | ü |  |  |  | Awaiting risk mitigation measures from importing NPPO
Prunus cuttings | US | [6 empty] | Awaiting risk mitigation measures from importing NPPO
Pyrus and Cydonia cuttings | US | [6 empty] | Provided comments to the US on PRAs May 2026
Radish | US |  | 2021 |  |  |  |  | Application under assessment
Spring onion | US |  | 2021 |  |  |  |  | Application under assessment
Strawberry | Thailand |  | 2022 |  | ü |  |  | Audit required prior to completion of access process
Strawberry | Taiwan |  | 2024 |  | ü |  |  | Application under assessment