## Sheet1
Commodity | Country | Status |  |  |  |  | On hold | Action required/Notes
|  | Dossier under development | Year dosser submitted | Pest Risk Assessment (PRA) under review | Audit required? | Legislation drafting
Apple | Philippines |  | 2016 | ü | ü |  |  | Providing answers to additional questions from importing NPPO
Apple | Vietnam |  | 2025 |  | ü |  |  | Dossier submitted June 2025. Application under assessment.
Apple | China |  | 2022 |  | ü |  | ü | China will only assess 1 application from a country at a time
Blueberry | Thailand |  | 2023 |  | ü | ü |  | Audit required prior to completion of access process
Celery | US |  | 2021 | ü |  | ü |  | UK consented to risk mitigation measures
Cherry | South Korea |  | 2022 | ü | ü |  |  | Providing answers to additional questions from importing NPPO
Cherry | Vietnam |  | 2023 | ü | ü |  |  | Awaiting Importing NPPOs review of UK draft mitigation measures
Cherry | China |  | 2021 | ü | ü |  |  | Awaiting importing NPPOs review of UK draft mitigation measures
Cherry | Brazil |  | 2023 |  | ? |  |  | Application under assessment
Cherry | Thailand |  |  |  | ü |  | ü | Not a priority for exporter currently
Date palm plants | Paraguay | ü | [5 empty] | Dossier under development
Malus cuttings | USA |  |  | ü |  |  |  | Awaiting risk mitigation measures from importing NPPO
Musa acuminata | Colombia |  | 2025 | ü |  |  |  | Dossier submitted October 2025. Application under assessment
Cherry | India | [5 empty] | ü | Providing answers to additional questions from importing NPPO
Poplar logs | India |  | 2016 |  |  |  |  | Providing answers to additional questions from importing NPPO
Potato mini tubers from Scotland | US |  | 2009 | ü |  |  |  | Awaiting risk mitigation measures from importing NPPO
Radish | US |  | 2021 |  |  |  |  | Application under assessment
Spring onion | US |  | 2021 |  |  |  |  | Application under assessment
Strawberry | Thailand |  | 2022 |  | ü |  |  | Application under assessment
Strawberry | Taiwan |  | 2024 |  | ü |  |  | Application under assessment
Strawberry | South Korea |  |  |  | ü |  | ü | Awaiting confirmation of audit costs to be covered before submitting